## SUMMARY
Caisley Developments Ltd.
X8 Richards — Unit 3401, 1111 Richards Street, Vancouver BC V6B 0S3
CLIENT ESTIMATE
Date: 2026-07-21
Drawings: Gaile Guevara Studio, ID0.00-ID1.51, 'Permit Plan Draft', printed 2025-09-10
NOT CONFIRMED AS THE CURRENT DRAWING SET — priced as issued above
| Division | Amount
| DIVISION 1 - GENERAL REQUIREMENTS | 70216.16
| DIVISION 2 - SITEWORK | 25918.96
| DIVISION 5 - METALS | 0
| DIVISION 6 - WOOD AND PLASTICS | 3767.88
| DIVISION 8 - DOORS AND WINDOWS | 10650
| DIVISION 9 - FINISHES | 236542.08
| DIVISION 10 - SPECIALTIES | 16021.64
| DIVISION 11 - EQUIPMENT | 0
| DIVISION 12 - FURNISHINGS | 0
| DIVISION 15 - MECHANICAL | 63142.56
| DIVISION 16 - ELECTRICAL | 59221.64
| SUB-TOTAL | 485480.92
| CONTINGENCY / INFLATION @ 10.0% | 48548.092
| SUB-TOTAL INCLUDING CONTINGENCY | 534029.012
| CONTRACTOR'S FEE @ 13.0% | 69423.7716
| SUB-TOTAL INCLUDING FEE | 603452.7836
| GST @ 5.0% | 30172.6392
| TOTAL ESTIMATE | 633625.4227

## ASSUMPTIONS
Assumptions
1. | Priced from a set marked 'Permit Plan Draft', printed 2025-09-10 — ten months old at the date of this estimate and not a final permit issue. Numbers will move if the set has been revised.
2. | Scope area taken as 1,712.54 sq.ft. as stated on ID0.00. The cover splits this as Level 34: 1,381.30 and Level 35: 331.24, which does not appear consistent with the extent of work shown on the upper level plans. Total used, split not relied upon.
3. | Room areas and wall lengths are measured from the drawings. The title block states the drawings are not to be scaled and not to be used to calculate areas, so all quantities require verification on site before this estimate is relied upon.
4. | Grayed areas on ID1.20 are excluded from scope and are not priced.
5. | Programme assumed at 4 months. Site supervision and general requirements are duration-driven and will move with it.
6. | Existing tile floors and the drop ceiling to current extension are retained, per ID1.10 keynotes 15 and 22.
7. | Existing toilet retained per ID1.10 keynote 08.
8. | Building is 2019 construction (VBBL 2019, strata plan EPS7373), so hazardous materials risk is assumed low — but no survey has been sighted.
9. | Work assumed to proceed in an occupied building with restricted working hours, elevator booking, and no on-site waste bin or lay-down area.
10. | All labour estimated at a blended crew rate of $73.88/hr (2026 basis); actual billing at individual role rates.

## EXCLUSIONS
Exclusions
1. | Appliances — by owner
2. | Furniture, window coverings and styling
3. | Balcony and any exterior works
4. | Structural alterations — no structural drawings issued
5. | Hazardous materials survey and abatement
6. | Strata legal, engineering review or permit application fees
7. | Design fees and consultant coordination beyond normal GC duties
8. | Any work outside the areas shown in scope on ID1.20

## QUESTIONS
Open questions
1. | Is this the current drawing set? The set is marked 'Permit Plan Draft' and printed 2025-09-10. Assumed meanwhile: Priced as issued 2025-09-10 Affects: entire estimate
2. | The cover splits proposed area as Level 34: 1,381.30 sq.ft. and Level 35: 331.24 sq.ft., but the upper level plans show extensive work in the W.I.C., ppal ensuite and study. Please confirm the scope area per level. Assumed meanwhile: Total 1,712.54 sq.ft. used; per-level split not relied upon Affects: all area-based lines
3. | PF08 appears as a tag on ID1.20 but is not listed in the fixture keytag legend. What is it? Assumed meanwhile: Not priced separately Affects: 15.2
4. | Microtopping colour and product are TBD. Which system, and is a mock-up required? Assumed meanwhile: Mid-range specialist system, no mock-up Affects: 9.14
5. | What is the total extent of microtopping to walls, as opposed to floors? Wall area drives this line far more than floor area. Assumed meanwhile: Approximately 1,800 sq.ft. total measured off the finishes plan Affects: 9.14
6. | Are plumbing fixtures supplied by owner or contractor, and is there a specification or budget? Assumed meanwhile: Contractor-supplied against a $28,000 provisional cost Affects: 15.2
7. | Is there an electrical design, or a fixture schedule? None is included in this set. Assumed meanwhile: Carried as provisional cost Affects: 16.1, 16.3
8. | Has the strata confirmed working hours, elevator booking procedure, deposit and any hoarding requirements? Assumed meanwhile: Standard downtown Vancouver strata conditions Affects: Division 1
9. | Confirm solid wood flooring species, grade and whether it is site-finished or prefinished. Assumed meanwhile: Prefinished engineered-equivalent solid at $28/sq.ft. supplied and installed Affects: 9.5
10. | Is a hazardous materials survey available? Assumed low risk given 2019 construction. Assumed meanwhile: No abatement required Affects: excluded