## SUMMARY
Caisley Developments Ltd.
X8 Richards — Unit 3401, 1111 Richards Street, Vancouver BC V6B 0S3
CLIENT ESTIMATE
Date: 2026-07-21
Drawings: Gaile Guevara Studio, ID0.00-ID1.51, 'Permit Plan Draft', printed 2025-09-10
NOT CONFIRMED AS THE CURRENT DRAWING SET — priced as issued above
| Division | Amount
| DIVISION 1 - GENERAL REQUIREMENTS | 70216.16
| DIVISION 2 - SITEWORK | 25918.96
| DIVISION 5 - METALS | 0
| DIVISION 6 - WOOD AND PLASTICS | 3767.88
| DIVISION 8 - DOORS AND WINDOWS | 10650
| DIVISION 9 - FINISHES | 236542.08
| DIVISION 10 - SPECIALTIES | 16021.64
| DIVISION 11 - EQUIPMENT | 0
| DIVISION 12 - FURNISHINGS | 0
| DIVISION 15 - MECHANICAL | 63142.56
| DIVISION 16 - ELECTRICAL | 59221.64
| SUB-TOTAL | 485480.92
| CONTINGENCY / INFLATION @ 10.0% | 48548.092
| SUB-TOTAL INCLUDING CONTINGENCY | 534029.012
| CONTRACTOR'S FEE @ 13.0% | 69423.7716
| SUB-TOTAL INCLUDING FEE | 603452.7836
| GST @ 5.0% | 30172.6392
| TOTAL ESTIMATE | 633625.4227

## ESTIMATE DETAILS
Caisley Developments Ltd.
X8 Richards — Unit 3401, 1111 Richards Street, Vancouver BC V6B 0S3
INTERNAL WORKING ESTIMATE
Date: 2026-07-21
Drawings: Gaile Guevara Studio, ID0.00-ID1.51, 'Permit Plan Draft', printed 2025-09-10
NOT CONFIRMED AS THE CURRENT DRAWING SET — priced as issued above
Code | Description | Qty | Unit | Rate | Material/Sub | Hours | Labour | Type | Source
DIVISION 1 - GENERAL REQUIREMENTS
1.1 | Site setup, protection of strata common property, elevator lobby and corridor protection | 1 | allowance | 6000 | 6000 | 16 | 1182.08 | Self-perform | strata highrise condition
1.1 | Elevator booking, material hoisting and restricted-hours premium | 1 | allowance | 8000 | 8000 | 8 | 591.04 | P.C. allowance | strata highrise condition
1.2 | Temporary dust walls and protection of retained finishes | 1 | allowance | 4500 | 4500 | 24 | 1773.12 | Self-perform | ID1.10 keynotes 15, 22
1.3 | Rentals, equipment and site facilities | 4 | months | 875 | 3500 |  |  | Self-perform | assumed 4-month programme
1.5 | Strata damage deposit, move-in/out and administration fees | 1 | P.C. | 5000 | 5000 | 2 | 147.76 | P.C. allowance | strata bylaw — to confirm
1.5 | Hazardous materials abatement |  |  |  | NOT INCLUDED — no survey available |  |  | Excluded | 2019 building, low risk but unconfirmed
1.6 | Waste removal — bagged to loading bay, no on-site bin available | 12 | loads | 650 | 7800 | 36 | 2659.68 | Self-perform | no street access
1.7 | Final clean | 1 | allowance | 3500 | 3500 |  |  | Subtrade | standard
1.8 | Site supervision — 20 hrs/week over 17.3 weeks | 346 | hours | 0 | 0 | 346 | 25562.48 | Self-perform | assumed 4-month programme
DIVISION 2 - SITEWORK
2.2 | Remove existing engineered wood flooring | 1050 | sq.ft. | 2.5 | 2625 | 21 | 1551.48 | Self-perform | ID1.10 keynote 21
2.2 | Remove interior partitions, closet walls and doors | 90 | lineal | 45 | 4050 | 36 | 2659.68 | Self-perform | ID1.10 keynotes 04, 09, 11, 12, 13, 14
2.2 | Remove existing millwork — W.I.C., vanities, closets, valance and integrated lighting | 1 | allowance | 8500 | 8500 | 48 | 3546.24 | Self-perform | ID1.10 keynotes 03, 07, 10, 25, 27, 29
2.2 | Remove existing plumbing fixtures — shower, bathtub, two vanities and sinks, kitchen faucet | 6 | at | 350 | 2100 | 12 | 886.56 | Self-perform | ID1.10 keynotes 05, 06, 07, 28
2.2 | Balcony and exterior works |  |  |  | NOT INCLUDED — outside scope area |  |  | Excluded | ID1.20 grayed area
DIVISION 5 - METALS
5.3 | Structural alterations |  |  |  | NOT INCLUDED — no structural drawings issued |  |  | Excluded | no structural in set
DIVISION 6 - WOOD AND PLASTICS
6.10 | Door hardware installation | 6 | doors | 0 | 0 | 9 | 664.92 | Self-perform | ID1.20 D1-D5
6.9 | Door installation — 6 leaves incl. sliding hardware | 6 | doors | 0 | 0 | 42 | 3102.96 | Self-perform | ID1.20 D1-D5
DIVISION 8 - DOORS AND WINDOWS
8.1 | D1 lower bedroom swing door 36" solid core paint grade | 1 | at | 850 | 850 |  |  | Quote | ID1.20
8.1 | D2 lower ensuite sliding door 32" solid core paint grade | 1 | at | 1400 | 1400 |  |  | Quote | ID1.20
8.1 | D3 ppal ensuite sliding door 52" solid core paint grade | 1 | at | 1900 | 1900 |  |  | Quote | ID1.20
8.1 | D4 ppal bedroom double swing door 70" — two solid core leaves | 1 | at | 2400 | 2400 |  |  | Quote | ID1.20
8.1 | D5 ppal bedroom W.I.C. sliding door 42" solid core paint grade | 1 | at | 1600 | 1600 |  |  | Quote | ID1.20
8.4 | Door hardware — sliding tracks, pulls, privacy sets | 1 | P.C. | 2500 | 2500 |  |  | P.C. allowance | no hardware schedule
DIVISION 9 - FINISHES
9.1 | New metal stud partitions, acoustic fire batt, 5/8" GWB both sides — types 01-04 | 90 | lineal | 145 | 13050 | 1 | 73.88 | Subtrade | ID1.20 assemblies 01-04
9.1 | Wet-area partitions and furring — 14mm WEDI vapour board to shower side — types W1-W4 | 55 | lineal | 210 | 11550 | 1 | 73.88 | Subtrade | ID1.20 assemblies W1-W4
9.1 | Drywall making-good to existing surfaces after demolition and device relocation | 1 | allowance | 9000 | 9000 | 1 | 73.88 | Subtrade | extent unknown until demo
9.12 | M01 lower ensuite custom millwork vanity | 1 | at | 9500 | 9500 | 1 | 73.88 | Subtrade | ID1.20
9.12 | M02 lower bedroom custom millwork closet and desk | 1 | at | 11000 | 11000 | 1 | 73.88 | Subtrade | ID1.20
9.12 | M02.1 lower kitchen custom wood extension for dining | 1 | at | 4500 | 4500 | 1 | 73.88 | Subtrade | ID1.20
9.12 | M03 upper ppal ensuite custom millwork vanity | 1 | at | 9500 | 9500 | 1 | 73.88 | Subtrade | ID1.20
9.12 | M04 upper ppal W.I.C. custom millwork closet — two runs | 2 | at | 7500 | 15000 | 1 | 73.88 | Subtrade | ID1.20
9.12 | M05 upper stairs custom millwork closet | 1 | at | 6500 | 6500 | 1 | 73.88 | Subtrade | ID1.20
9.12 | M06/M07 upper study custom millwork closets 1 and 2 | 2 | at | 7500 | 15000 | 1 | 73.88 | Subtrade | ID1.20
9.12 | Kitchen modifications — island side gable, pull-out drawers below oven, microwave relocation, cabinet door replacement, top reveal flush | 1 | allowance | 12500 | 12500 | 1 | 73.88 | Subtrade | ID1.20 keynotes 02-06
9.13 | Stone counters with integrated sinks — PF02 and PF07 | 2 | at | 7500 | 15000 | 1 | 73.88 | Subtrade | ID1.20 PF02, PF07
9.14 | Microtopping CONC01 to floors, walls and shower step riser — specialist applied finish | 1800 | sq.ft. | 32 | 57600 | 1 | 73.88 | Subtrade | ID1.40 keynotes 02, 03, 05
9.14 | Microtopping CONC01 over existing kitchen cabinetry fronts | 120 | sq.ft. | 38 | 4560 | 1 | 73.88 | Subtrade | ID1.40 keynote 04
9.3 | Interior painting PT01 — walls and ceilings to match existing colour | 4500 | sq.ft. | 2.6 | 11700 | 1 | 73.88 | Subtrade | ID1.40 finishes legend
9.5 | Solid wood flooring WD01 — supply and install | 1050 | sq.ft. | 28 | 29400 | 1 | 73.88 | Subtrade | ID1.40 WD01 zones
DIVISION 10 - SPECIALTIES
10.2 | Bathroom accessories | 1 | P.C. | 3500 | 3500 | 1 | 73.88 | P.C. allowance | no accessory schedule
10.3 | Mirrors | 1 | P.C. | 2800 | 2800 | 1 | 73.88 | P.C. allowance | no mirror schedule
10.4 | G1 frameless translucent Starphire tempered shower glazing | 1 | allowance | 9500 | 9500 | 1 | 73.88 | Subtrade | ID1.20 G1
DIVISION 11 - EQUIPMENT
11.2 | Appliances |  |  |  | BY OWNER |  |  | Excluded | not scheduled
DIVISION 12 - FURNISHINGS
12 | Furniture, window coverings and styling |  |  |  | NOT INCLUDED |  |  | Excluded | not scheduled
DIVISION 15 - MECHANICAL
15.1 | Plumbing rough-in and relocation — 8 fixture positions | 8 | units | 1782 | 14256 | 8 | 591.04 | Subtrade | ID1.20 PF01-PF07
15.1 | Raise floor level to shower room area, build-up and drain relocation | 1 | allowance | 3500 | 3500 | 1 | 73.88 | Subtrade | ID1.20 keynote 01; ID1.10 keynote 16
15.2 | Plumbing fixtures supply — wall-mount faucets, shower bar, controls, head | 1 | P.C. | 28000 | 28000 | 1 | 73.88 | P.C. allowance | no fixture specification issued
15.5 | Sprinkler head relocation — licensed contractor, occupied sprinklered highrise | 1 | P.C. | 12000 | 12000 | 1 | 73.88 | P.C. allowance | ID1.51
15.6 | HVAC modifications — ceiling fan relocation, diffuser adjustment | 1 | allowance | 4500 | 4500 | 1 | 73.88 | Subtrade | ID1.11 keynote 02
DIVISION 16 - ELECTRICAL
16.1 | Electrical rough-in, device relocation — switches, outlets, keypads, fire alarm, access points, AV | 1 | P.C. | 32000 | 32000 | 1 | 73.88 | P.C. allowance | ID1.30; no electrical design issued
16.3 | Light fixtures supply and relocation — recessed and surface spot lights | 1 | P.C. | 18000 | 18000 | 1 | 73.88 | P.C. allowance | ID1.11, ID1.21
16.4 | Low voltage — AV outlets, automatic shade keypads | 1 | P.C. | 9000 | 9000 | 1 | 73.88 | P.C. allowance | ID1.10 keynotes 19, 23

## ASSUMPTIONS
Assumptions
1. | Priced from a set marked 'Permit Plan Draft', printed 2025-09-10 — ten months old at the date of this estimate and not a final permit issue. Numbers will move if the set has been revised.
2. | Scope area taken as 1,712.54 sq.ft. as stated on ID0.00. The cover splits this as Level 34: 1,381.30 and Level 35: 331.24, which does not appear consistent with the extent of work shown on the upper level plans. Total used, split not relied upon.
3. | Room areas and wall lengths are measured from the drawings. The title block states the drawings are not to be scaled and not to be used to calculate areas, so all quantities require verification on site before this estimate is relied upon.
4. | Grayed areas on ID1.20 are excluded from scope and are not priced.
5. | Programme assumed at 4 months. Site supervision and general requirements are duration-driven and will move with it.
6. | Existing tile floors and the drop ceiling to current extension are retained, per ID1.10 keynotes 15 and 22.
7. | Existing toilet retained per ID1.10 keynote 08.
8. | Building is 2019 construction (VBBL 2019, strata plan EPS7373), so hazardous materials risk is assumed low — but no survey has been sighted.
9. | Work assumed to proceed in an occupied building with restricted working hours, elevator booking, and no on-site waste bin or lay-down area.
10. | All labour estimated at a blended crew rate of $73.88/hr (2026 basis); actual billing at individual role rates.

## EXCLUSIONS
Exclusions
1. | Appliances — by owner
2. | Furniture, window coverings and styling
3. | Balcony and any exterior works
4. | Structural alterations — no structural drawings issued
5. | Hazardous materials survey and abatement
6. | Strata legal, engineering review or permit application fees
7. | Design fees and consultant coordination beyond normal GC duties
8. | Any work outside the areas shown in scope on ID1.20

## QUESTIONS
Open questions
1. | Is this the current drawing set? The set is marked 'Permit Plan Draft' and printed 2025-09-10. Assumed meanwhile: Priced as issued 2025-09-10 Affects: entire estimate
2. | The cover splits proposed area as Level 34: 1,381.30 sq.ft. and Level 35: 331.24 sq.ft., but the upper level plans show extensive work in the W.I.C., ppal ensuite and study. Please confirm the scope area per level. Assumed meanwhile: Total 1,712.54 sq.ft. used; per-level split not relied upon Affects: all area-based lines
3. | PF08 appears as a tag on ID1.20 but is not listed in the fixture keytag legend. What is it? Assumed meanwhile: Not priced separately Affects: 15.2
4. | Microtopping colour and product are TBD. Which system, and is a mock-up required? Assumed meanwhile: Mid-range specialist system, no mock-up Affects: 9.14
5. | What is the total extent of microtopping to walls, as opposed to floors? Wall area drives this line far more than floor area. Assumed meanwhile: Approximately 1,800 sq.ft. total measured off the finishes plan Affects: 9.14
6. | Are plumbing fixtures supplied by owner or contractor, and is there a specification or budget? Assumed meanwhile: Contractor-supplied against a $28,000 provisional cost Affects: 15.2
7. | Is there an electrical design, or a fixture schedule? None is included in this set. Assumed meanwhile: Carried as provisional cost Affects: 16.1, 16.3
8. | Has the strata confirmed working hours, elevator booking procedure, deposit and any hoarding requirements? Assumed meanwhile: Standard downtown Vancouver strata conditions Affects: Division 1
9. | Confirm solid wood flooring species, grade and whether it is site-finished or prefinished. Assumed meanwhile: Prefinished engineered-equivalent solid at $28/sq.ft. supplied and installed Affects: 9.5
10. | Is a hazardous materials survey available? Assumed low risk given 2019 construction. Assumed meanwhile: No abatement required Affects: excluded

## RISK
Change-order exposure
1. | Microtopping (9.14) — largest single finishes line — Rate is unverified against a Caisley project. Applied over existing substrates whose condition is unknown until demolition; failure or adhesion issues mean full removal and redo. Wall area was measured off a drawing marked do-not-scale.
2. | Custom millwork (9.12) — nine separate items, ~$71,000 — No millwork elevations, sections or specifications exist in the set. Priced from plan tags alone. This is the line most likely to move once shop drawings are produced.
3. | Electrical (16.1, 16.3, 16.4) — $59,000 of provisional cost — No electrical design in the set. Extensive device relocation shown on ID1.30 but no circuiting, no panel information, and no confirmation the existing service supports the changes.
4. | Strata and highrise access constraints (Division 1) — Elevator booking, restricted hours, no lay-down space and bagged waste removal are all productivity penalties that Caisley's historical rates — derived from detached house work — do not carry.
5. | Drywall making-good after demolition — Carried as a $9,000 allowance. Extent is genuinely unknowable until walls are opened, and ID1.10 instructs the contractor to verify existing conditions on site.
6. | Sprinkler relocation (15.5) — Occupied sprinklered highrise. Requires a licensed contractor, strata coordination and system shutdown windows. Provisional only — no design issued.
7. | Drawing set is ten months old and marked draft — Design development between issues routinely moves numbers. This estimate should be re-priced against the current set before it is relied upon commercially.